SOFTWARE EXECUTION PLAN

Wedding Management Suite

Full Software Development Lifecycle: Requirements to Operations

| Document Version: | 2.1 |
| --- | --- |
| Document Date: | August 12, 2026 |
| Project Name: | Wedding Management Suite |
| Based on: | BRD v1.0; User Story Document v1.0 |
| Lifecycle Model: | Stage-gated SDLC with Agile construction (2-week sprints) |
| Product Engineer: |  |
| Document Status: | Draft for Review |
| Classification: | Internal Use |

# TABLE OF CONTENTS

# 1. DOCUMENT CONTROL

## 1.1 Document History

| Version | Date | Author | Description | Approver |
| --- | --- | --- | --- | --- |
| 1.0 | 2026-08-12 | Business Analyst | Execution & Business Implementation Plan (business-oriented) | Superseded |
| 2.0 | 2026-08-12 | Business Analysis Team | Complete rewrite as a full-SDLC software execution plan: requirements engineering through operations | Superseded |
| 2.1 | 2026-08-12 | Product Engineer | Organisation model consolidated to a single product-engineering role with procured external services; schedule re-baselined to sustainable single-track capacity; full scope retained | Pending |

## 1.2 Review and Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Product Engineer |  |  |  |
| Legal / Compliance Advisor (external) |  |  |  |

## 1.3 Referenced Documents

| Document | Version | Role in This Plan |
| --- | --- | --- |
| Business Requirements Document | 1.0 | Source of BR/FR/NFR baselines; acceptance criteria; risk set |
| User Story Document | 1.0 | Construction backlog: 15 epics, 49 stories, 318 story points, MoSCoW priorities |

# 2. INTRODUCTION

## 2.1 Purpose

This plan defines how the Wedding Management Suite is engineered, from requirements baselining through architecture, construction, verification, release, and live operation. It is a software development plan: every section corresponds to a discipline of the software development lifecycle (SDLC), with entry criteria, activities, work products, and exit criteria for each stage, and with the project-management scaffolding (work breakdown, schedule, staffing, configuration management, risk, and quality) that carries the product across all stages.

## 2.2 Scope

In scope: all engineering and engineering-adjacent activity required to take BRD v1.0 to a launched, operated product — five surfaces (couple/planner console, guest surfaces, vendor surface, public site, back-office), seventeen functional modules, and the platform beneath them. Out of scope: commercial strategy, marketing execution, and pricing analysis, which are governed at steering level; this plan carries only their engineering dependencies (billing implementation, launch gates).

## 2.3 Lifecycle Model Selection

The programme uses a stage-gated SDLC with Agile construction. Requirements and architecture are engineered and baselined up front (Stages 1-2) because three properties of this product punish rework discovered late: the guest performance budget constrains the rendering architecture; tenant isolation and the three-pattern access model constrain the data layer; and single-source generation constrains every module's shape. Construction (Stage 3) then proceeds in two-week sprints against the story backlog, in six build increments, each closing with verification activities from Stage 4 rather than deferring all testing to the end. Release (Stage 5) and Operations (Stage 6) overlap construction from the first pilot onward. The model is therefore: engineer the foundations sequentially, build and verify iteratively, release incrementally.

## 2.4 SDLC Stage Overview and Gates

| Stage | Discipline | Timing | Gate (must pass to proceed) |
| --- | --- | --- | --- |
| 1 | Requirements Engineering | Weeks 0-2 (complete); continuous change control thereafter | G1: Requirements Baseline — BRD/US signed, traceability established |
| 2 | System Design & Architecture | Weeks 1-6; design refresh at each increment | G2: Architecture Baseline — ADRs ratified, performance budget proven on prototype |
| 3 | Construction | Sprints S2-S33 (Weeks 3-66), six increments | G3 (per increment): increment exit criteria demonstrated on real data/devices |
| 4 | Verification & Validation | Continuous from S2; system V&V Weeks 67-72 | G4: V&V Complete — audits passed, NFRs field-verified, UAT accepted |
| 5 | Release & Deployment | Pilot releases from Week 32; production launch after G4 | G5: Release Gate — legal, commercial, quality, validation gates passed |
| 6 | Operations & Maintenance | From first pilot; steady state post-launch | Operational acceptance review at T+8 weeks |

Stages 1-2 are engineered sequentially and gated. Stages 3-4 interleave sprint by sprint. Stage 5 runs incrementally (pilot channel) before the production launch event. Timing weeks align to the master schedule in Section 9.

# 3. STAGE 1: REQUIREMENTS ENGINEERING

## 3.1 Objectives

Establish a complete, testable, change-controlled requirements baseline, and keep it authoritative for the life of the programme. This stage is substantially complete: BRD v1.0 (30 business requirements, 65 functional requirements, non-functional targets) and the User Story Document v1.0 (49 stories, acceptance criteria, MoSCoW, story points) constitute the baseline. What remains is baselining mechanics and continuous requirements management.

## 3.2 Entry Criteria

- Product concept and scope boundaries agreed (BRD Sections 3-6)

- Stakeholders and external advisors identified (BRD Section 5)

## 3.3 Activities

- Requirements sign-off: BRD v1.0 and US v1.0 formally approved and recorded as the requirements baseline (Week 0)

- Traceability establishment: machine-readable Requirements Traceability Matrix (RTM) linking BR to FR to US to (later) design components, test cases, and releases; RTM lives in the tracker, not in a document

- Testability review: QA Lead reviews every acceptance criterion for verifiability; ambiguous criteria are rewritten before construction consumes them (e.g. 'approximately ninety seconds' bound to a measured p50 target)

- Non-functional decomposition: each NFR assigned a measurement owner, an instrument (field monitoring, device lab, load rig), and the stage at which it is first measurable

- Open-decision register: launch jurisdictions (blocks compliance requirements), commercial model (blocks billing requirements), product name — each with owner and need-by date

- Requirements change control from baseline day: changes enter as change requests, are impact-assessed against the RTM (scope, schedule, test), and are dispositioned at the fortnightly change-control review (Section 11.2)

## 3.4 Work Products

- Signed requirements baseline (BRD v1.0, US v1.0)

- Requirements Traceability Matrix (living, in-tracker)

- NFR measurement plan

- Open-decision register

- Change request log

## 3.5 Exit Criteria (Gate G1)

- Baseline signed; RTM populated for 100% of BRs, FRs, and stories

- Every story's acceptance criteria confirmed testable by QA

- Every NFR has an owner, an instrument, and a first-measurable stage

- Change control operating (review cadence scheduled, workflow live in tracker)

# 4. STAGE 2: SYSTEM DESIGN AND ARCHITECTURE

## 4.1 Objectives

Produce and ratify the architecture and detailed designs that the entire construction stage builds on. Every decision below is recorded as an Architecture Decision Record (ADR): context, options, decision, consequences. The architecture baseline (Gate G2) is the set of accepted ADRs plus the proven performance prototype.

## 4.2 Entry Criteria

- Gate G1 passed (requirements baseline)

- Engineering environment mobilised (Section 5.2)

## 4.3 Architectural Design Activities

### 4.3.1 System Architecture

- ADR-001 System decomposition: modular monolith with clean module boundaries (17 functional modules over one data model) versus microservices; operational simplicity and the single-data-object principle drive the recommendation toward the modular monolith with extraction seams

- ADR-002 API architecture: one documented API consumed by all five surfaces (API-first per BRD Section 11.3); contract style (REST/JSON with OpenAPI specification), versioning policy, error model, idempotency keys for all mutating guest-surface calls

- ADR-003 Rendering architecture (the critical-path decision): static shell with tokenised client fetch versus edge-side rendering for guest surfaces; decided by a two-week spike measured against the guest performance budget (FCP under 2.0s p75, mid-range Android, 3G) on a physical device over a throttled network; prototype evidence attached to the ADR

- ADR-004 Multi-tenancy and isolation: tenant scoping enforced in the data-access layer beneath the API (BRD NFR/security); row-level scoping strategy, cross-tenant test harness design

- ADR-005 Asynchronous work: job queue topology for dispatch, reminders, media variants, aggregate maintenance, domain polling, archival; idempotency, retry with backoff, dead-letter queues, operator visibility

- ADR-006 Data store selection and aggregate strategy: primary relational store; RSVP aggregates maintained transactionally as aggregates (never per-view scans); hot-path indexes (household token, wedding slug/custom domain, recipient delivery state)

- ADR-007 Media pipeline: signed direct uploads, asynchronous variant generation, EXIF/location stripping on ingest, server-side audio normalisation for voice notes

- ADR-008 Sending architecture: provider selection, dedicated warmed domain, webhook ingestion for per-recipient delivery states, suppression store, throttled dispatch

- ADR-009 Caching and CDN strategy: guest surfaces server-rendered and CDN-cached with per-household personalisation strategy (follows ADR-003), cache invalidation on wedding-data change (the single-source correctness mechanism)

- ADR-010 AuthN/AuthZ: account sessions (email/password, Apple, Google), 128-bit+ non-sequential revocable link tokens, permission matrix implementation for the three access patterns, grant evaluation

### 4.3.2 Data Design

- Logical data model covering the entity set of BRD Section 10.1 (wedding, membership, event, household, guest, RSVP, message/recipient, site, media, seating, accommodation, inventory, ledger, vendor, guestbook, audit)

- Physical schema with migration strategy (forward-only, reversible-by-migration), soft-delete versus hard-delete mapping to the retention table (BRD 10.2), archive-sealing representation

- Privacy-by-design review of the schema: tier and contributor fields structurally excluded from guest-facing query paths; special-category fields (allergy, accessibility) isolated and access-restricted

### 4.3.3 Interface and Experience Design

- Design system: tokens, components, accessibility-safe theme constraint system (no permitted combination fails contrast) — precedes site-builder construction

- Six to eight site themes designed against the constraint system; two delivered in Stage 2 as the design-system proof

- UX flows with prototypes for the reputation-forming paths: onboarding, import, RSVP (with screen-reader pass), seating canvas, guestbook composer and reading experience

- API contract (OpenAPI) published to the team before each increment's construction begins; frontend and backend build to the contract

### 4.3.4 Security and Compliance Design

- Threat model (STRIDE) across the five surfaces; link-token abuse, cross-tenant access, media abuse, and impersonation paths explicitly modelled

- Data-protection design review with counsel: processor/controller boundaries in the data flows, data-subject request paths for account-less guests, deletion propagation design including backups

- Audit design: workspace activity log and staff audit log as append-only structures

## 4.4 Design Reviews

- Architecture review: each ADR is closed with a written decision record at end of Week 5; an independent external reviewer is procured for ADR-003 (rendering) and ADR-004 (tenant isolation), the two decisions with the highest cost of error

- Each increment opens with a detailed-design review for its modules (design-before-build within construction); designs are lightweight design docs linked from the RTM

- Security design review, conducted against the threat model and recorded, is part of Gate G2

## 4.5 Work Products

- Accepted ADR set (ADR-001 to ADR-010, extended as needed)

- Rendering prototype with measured performance evidence

- OpenAPI contract v1

- Logical and physical data model; migration playbook

- Design system with two proven themes

- Threat model and security design review record

## 4.6 Exit Criteria (Gate G2)

- All foundation ADRs accepted; no open 'blocking' design questions in the register

- Rendering prototype meets the performance budget on physical hardware over throttled 3G

- Cross-tenant isolation harness proves scoping in the data-access layer

- OpenAPI v1 published; data model reviewed; security design review signed

# 5. STAGE 3: CONSTRUCTION

## 5.1 Objectives

Implement the 49-story backlog across six build increments, with engineering practices that keep quality in-line (built in, not inspected in at the end). Construction consumes the baselined requirements and the ratified architecture; it does not relitigate them outside change control.

## 5.2 Engineering Environment

| Concern | Standard |
| --- | --- |
| Version control | Single monorepo; trunk-based development with short-lived feature branches (under 2 days) |
| Change review | Every change lands via pull request against a structured review checklist; changes touching the permission matrix, data-access layer, or sending paths additionally pass a dedicated critical-path checklist (isolation, privacy, idempotency) before merge |
| Continuous integration | On every PR: build, lint, type-check, unit tests, integration tests, schema-migration check, contract check against OpenAPI; merge blocked on red |
| Quality gates in CI | Release-blocking suites run on main: timezone rendering, contribution-privacy (all grant combinations), tier-invisibility, tenant-isolation, accessibility lint |
| Definition of Ready | Story has testable acceptance criteria, design linkage, dependencies cleared, and a point estimate |
| Definition of Done | Acceptance criteria demonstrably pass; tests written (unit + integration; E2E for guest-critical paths); accessibility checks pass; preview-as-household verified for guest-visible changes; documentation and RTM updated; deployed to staging |
| Coding standards | Language style guides enforced by linters; no hand-rolled crypto; feature flags for incomplete work on trunk |
| Secrets & config | Twelve-factor configuration; secrets in a managed vault; no secrets in the repository |

## 5.3 Sprint Cadence and Capacity

Construction runs in two-week sprints S2-S33 (S1 is consumed by Stage 2 alongside engineering-platform setup). The backlog totals 318 story points across 49 stories; the planning assumption is a sustained velocity of 9-11 points per sprint on a single development track, calibrated against actuals at Sprint 4 and re-baselined then. Sprint structure: planning against the Definition of Ready, a mid-sprint checkpoint against the sprint goal, and a closing review that records a working-software demonstration against acceptance criteria plus a written retrospective note. MoSCoW priority governs any within-sprint scope pressure: Must Have stories are never traded for Should Have, and schedule pressure is absorbed by the timeline, not by scope.

## 5.4 Build Increment Plan

Each increment ends with a G3 gate: its exit criteria demonstrated on real data and physical devices, and its verification activities (Section 6) complete for the increment's scope.

| Increment | Sprints (Weeks) | Backlog | Points | G3 Exit Demonstration |
| --- | --- | --- | --- | --- |
| I1: Foundation | S2-S7 (Wk 3-14) | US-001..014 excl. US-008; US-049 skeleton | ~62 | Workspace + planner role live; 200-row real import clean after one pass; events timezone-correct |
| I2: Public Loop | S8-S16 (Wk 15-32) | US-018, US-020..026, US-028..031 | ~85 | Couple publishes unaided; household RSVP on physical mid-range Android; 200-send >98% delivered with per-recipient states |
| I3: Operations | S17-S22 (Wk 33-44) | US-015, US-019, US-027, US-032..039 | ~63 | Real budget incl. contributors; vendor invoice submitted-to-accepted; catering export accepted by a real caterer; custom domain live |
| I4: Logistics | S23-S27 (Wk 45-54) | US-008, US-040..045 | ~44 | Dry-run wedding day from coordinator view; guest seat view on phone; 60fps canvas at 300 guests |
| I5: Sentiment & Record | S28-S33 (Wk 55-66) | US-046..049 full scope (guestbook, photos, archive, export, back-office completion) | ~64 | Voice note via printed QR on physical devices; archive seals; every category exports; abuse queue and DSR tooling live |
| I6: Hardening | S34-S36 (Wk 67-72) | No new stories — verification only (Stage 4 system V&V) | 0 | Gate G4 evidence pack complete |

Story-number ranges reference the User Story Document v1.0; points are indicative allocations of the 318-point backlog and are re-estimated at each increment's planning. Sprint spans reflect the calibrated single-track velocity assumption and are re-baselined at Sprint 4.

## 5.5 Technical Debt and Refactoring Policy

- A visible debt register is maintained; each sprint reserves approximately 15% capacity for debt retirement, defect burn-down, and platform work

- Debt items that threaten a release-blocking suite (isolation, privacy, timezone) are scheduled immediately, not registered

- Increment boundaries include a short stabilisation window: no new stories enter the final two days before a G3 demonstration

# 6. STAGE 4: VERIFICATION AND VALIDATION

## 6.1 Test Strategy

Testing follows the test pyramid, runs continuously from the first construction sprint, and culminates in a system verification and validation stage (increment I6). Verification asks 'did we build it right' against the FR/NFR baseline; validation asks 'did we build the right thing' through pilot weddings against real use.

| Level | Scope | Automation | When | Owner |
| --- | --- | --- | --- | --- |
| Unit | Module logic: permission evaluation, aggregate maths, date/timezone handling, token generation | Fully automated, per PR | Every change | Product Engineer |
| Integration | API against contract; data-access isolation; queue/job behaviour; webhook ingestion | Automated in CI | Every change | Product Engineer |
| System / E2E | Cross-surface journeys: import→invite→RSVP→seat→export; browser automation on the guest path | Automated suite on main + nightly | Continuous from I2 | Product Engineer |
| Performance | FCP budget, RSVP round trip, canvas frame rate, dispatch throughput, aggregate latency | Device-lab harness + load rig | Each increment; full pass in I6 | Product Engineer |
| Security | Isolation harness, authZ matrix tests, dependency scanning, secrets scanning; external penetration test | CI scanners continuous; pen test in I6 | Continuous + I6 | Product Engineer (external assessor at I6) |
| Accessibility | Automated axe checks in CI; manual screen-reader passes; independent WCAG 2.2 AA audit | CI + manual + external audit | Continuous; audit in I6 | Product Engineer (external auditor at I6) |
| UAT / Validation | Pilot weddings executing real scenarios per BRD Section 15.2 | Manual, scripted scenarios | I2 onward; formal acceptance in I6 | Product Engineer with pilot couples |

## 6.2 Release-Blocking Test Suites

- Timezone suite: every surface renders event times correctly across timezone permutations (wrong time is a release-blocking defect class per BRD)

- Contribution-privacy suite: contributor data invisible to every non-Owner role under all grant combinations

- Tier-invisibility suite: tier data absent from all guest-facing surfaces and exports

- Tenant-isolation suite: cross-tenant access attempts fail at the data-access layer

- These four suites run on every merge to main and gate every release without exception

## 6.3 Test Environments and Data

- Test data: synthetic wedding generator (configurable households, events, RSVP states) plus anonymised real-shape import fixtures; no production personal data in lower environments

- Device lab: physical mid-range Android reference devices, iOS devices, and screen readers; network throttling to 3G profiles for all guest-path verification

- Load rig: seasonal-peak simulation (concurrent RSVP bursts, 200-household dispatches, media upload storms) run per increment sample and fully in I6

## 6.4 Defect Management

| Severity | Definition | Response |
| --- | --- | --- |
| S1 Critical | Wrong information reaching guests; data loss; cross-tenant exposure; guest surface down | Stop-the-line: fix before any release; incident review |
| S2 High | Release-blocking suite failure; NFR regression; broken Must Have acceptance criterion | Fix in current sprint; blocks increment gate |
| S3 Medium | Functional defect with workaround | Prioritised into next sprint |
| S4 Low | Cosmetic or minor | Backlog |

## 6.5 System V&V (Increment I6) and Gate G4

- Independent WCAG 2.2 AA audit (procured external service) across all guest flows including screen-reader RSVP; findings remediated and re-verified

- External penetration test (procured service); all critical and high findings closed, supplementing continuous automated scanning

- Full performance verification in the field: FCP p75 on physical devices over throttled 3G, RSVP p95, dispatch of 200 households under 5 minutes, 60fps canvas, voice-capture success above 99%

- Seasonal load test at peak-sized capacity

- UAT formal acceptance: pilot scenario pack executed per BRD 15.2; at least two pilot weddings completed end to end

- Gate G4 output: the V&V evidence pack — audit reports, test results, field measurements, UAT acceptance record

# 7. STAGE 5: RELEASE AND DEPLOYMENT

## 7.1 Environments

| Environment | Purpose | Deployment | Data |
| --- | --- | --- | --- |
| Development | Engineer workstations + ephemeral preview per PR | On push / per PR | Synthetic |
| Staging | Integration, E2E, device-lab testing; mirrors production topology | Continuous from main | Synthetic + fixtures |
| Pilot (production) | Real pilot weddings under feature flags | Continuous delivery with progressive exposure | Real (pilot tenants) |
| Production | General availability post-launch | Promoted releases | Real |

## 7.2 Deployment Pipeline

- Continuous delivery: every merge to main deploys to staging automatically after CI; production deploys are one-click promotions of a staged, versioned artefact

- Database migrations: forward-only, backwards-compatible with the previous release (expand/contract pattern); migration dry-run against a production-shaped snapshot in staging

- Feature flags: incomplete or increment-gated capability ships dark; pilot tenants are the first exposure ring, then percentage rollout

- Rollback: any release can be rolled back within minutes by re-promoting the previous artefact; migrations are never rolled back in place — contract steps ship only after the release stabilises

- Zero-downtime deploys for guest surfaces (the 99.95% availability target applies during deploys)

- Release notes generated per release and linked to stories and change requests in the RTM

## 7.3 Incremental Release Model

The pilot channel is live production from increment I2 onward: pilot weddings run on the real platform behind flags, which is what makes their evidence valid for validation. 'Launch' is therefore not a deployment event but a gate review that opens general availability.

## 7.4 Launch Gates (Gate G5)

| Gate | Condition | Evidence | Owner |
| --- | --- | --- | --- |
| G5.1 Legal | Compliance review complete; ToS, Privacy Policy, DPA, guest notices, retention policy in force | Counsel sign-off | Legal / Compliance |
| G5.2 Commercial | Commercial model decided; billing flows implemented and tested | Recorded decision; billing test results | Product Engineer |
| G5.3 Quality | Gate G4 evidence pack accepted | V&V evidence pack | Product Engineer |
| G5.4 Validation | At least two pilot weddings completed end to end with retrospectives | Pilot retrospectives | Product Engineer |

## 7.5 Launch Sequence

- T-4 weeks: G5 review convened; go/no-go recorded

- T-2 weeks: change freeze except fixes; status page live; monitoring thresholds tightened; support coverage windows published

- T-0: general availability opened; guest-surface attribution active

- T+2 weeks: stabilisation review (deliverability, availability, error budget, support volume, activation funnel)

- T+8 weeks: operational acceptance review; transition to steady-state operations (Stage 6)

# 8. STAGE 6: OPERATIONS AND MAINTENANCE

## 8.1 Service Level Objectives and Monitoring

- SLOs: guest surface availability 99.95% (externally probed); RSVP round trip under 1.0s p95; invitation delivery above 98%; dispatch of 200 households under 5 minutes

- Observability: structured logs, distributed traces on the API, metrics dashboards per surface; real-user monitoring on guest paths segmented by device class

- Alerting: paging on SLO burn, queue depth, certificate renewal failure, deliverability degradation, and error-rate anomalies; alert runbooks linked from every page

- Error budgets: SLO burn beyond budget pauses feature promotion in favour of reliability work

## 8.2 Incident Management

- Severity-classified incident process with a documented response runbook per alert; live-wedding-impacting incidents are always S1

- Status page updated for guest-visible impact; post-incident review within five working days with actions tracked to closure

- The printable fallback (exports, invitation PDFs) is the documented business-continuity path for sending or surface outages

## 8.3 Maintenance and Change

- Corrective (defects), adaptive (browser/OS window, provider API changes), perfective (Could Have backlog, pilot feedback), and preventive (debt register) maintenance all flow through the same sprint process and change control

- Dependency and security patching: automated update PRs; critical CVEs patched within 48 hours

- Annual pre-season load test and browser-matrix review before each wedding season

- Data lifecycle operations: archive sealing, retention enforcement, deletion propagation verification — audited quarterly

## 8.4 Support Operations

- Support runs on the back-office (built from increment I1, completed in I5): tenant search, audited impersonation, delivery and DNS diagnostics, abuse queue, data-subject request tooling

- Playbooks authored from pilot tickets; escalation matrix from support to engineering with S1/S2 definitions shared with Section 6.4

- Support KPIs: contacts per wedding (declining), first response time, resolution without engineering escalation

# 9. MASTER SCHEDULE AND WORK BREAKDOWN

## 9.1 Work Breakdown Structure

| WBS | Work Package | Stage | Weeks |
| --- | --- | --- | --- |
| 1.0 | Programme management, governance, change control | All | 0-72 |
| 2.0 | Requirements baselining, RTM, NFR measurement plan | 1 | 0-2 |
| 3.0 | Architecture: ADRs, rendering spike, data model, OpenAPI v1 | 2 | 1-5 |
| 3.1 | Design system + two themes; UX prototypes (RSVP, import, seating, guestbook) | 2 | 1-6 |
| 3.2 | Threat model, security & privacy design review | 2 | 3-6 |
| 4.0 | Engineering platform: CI/CD, environments, quality-gate suites, test data generator | 3 | 1-4 |
| 5.1 | Increment I1: Foundation build + verification | 3-4 | 3-14 |
| 5.2 | Increment I2: Public Loop build + verification | 3-4 | 15-32 |
| 5.3 | Increment I3: Operations build + verification | 3-4 | 33-44 |
| 5.4 | Increment I4: Logistics build + verification | 3-4 | 45-54 |
| 5.5 | Increment I5: Sentiment & Record build + verification | 3-4 | 55-66 |
| 6.0 | System V&V: audits, pen test, load test, field NFRs, UAT acceptance | 4 | 67-72 |
| 7.0 | Release engineering: pilot channel, flags, launch sequence | 5 | 15-72 |
| 8.0 | Operations build-out: monitoring, runbooks, support playbooks | 6 | 3-72 |
| 9.0 | Parallel business workstreams (engineering dependencies only): domain warm-up, counsel checkpoints, billing implementation, pilot onboarding | 1-6 | 0-72 |

## 9.2 Schedule Summary

Indicative dates assume mobilisation on 5 October 2026. Total duration approximately 72 weeks at the calibrated single-track velocity assumption; the schedule is re-baselined after Sprint 4 velocity calibration, and sequence and gate structure hold regardless of duration.

| Weeks | Sprints | Content | Gate |
| --- | --- | --- | --- |
| 0-2 | S1 (part) | Stage 1 close-out: baselining, RTM, testability review | G1 |
| 1-6 | S1 | Stage 2 architecture; engineering platform; I1 opens from Wk 3 | G2 (Wk 5-6) |
| 3-14 | S2-S7 | Increment I1: foundation | G3-I1 (Wk 14) |
| 15-32 | S8-S16 | Increment I2: the public loop; pilot channel opens | G3-I2 (Wk 32) |
| 33-44 | S17-S22 | Increment I3: operations modules; custom domains | G3-I3 (Wk 44) |
| 45-54 | S23-S27 | Increment I4: logistics; day-of dry run | G3-I4 (Wk 54) |
| 55-66 | S28-S33 | Increment I5: guestbook, photos, archive, back-office completion | G3-I5 (Wk 66) |
| 67-72 | S34-S36 | Increment I6: system V&V; launch gate review | G4 then G5 (Wk 72) |

## 9.3 Critical Path

- G1 → ADR-003 rendering spike → G2 → I2 guest-surface construction → first pilot sends (warmed domain dependency) → pilot weddings → G5.4 validation gate

- The sending-domain warm-up (WBS 9.0) starts Week 1 because it must complete before I2 production sends open the pilot channel

- Legal review (G5.1) and the commercial decision (G5.2) are the two non-engineering critical-path items; both are tracked in the open-decision register with hard need-by dates (commercial decision by end of I4)

# 10. ORGANISATION, ROLES AND RESPONSIBILITIES

## 10.1 Organisation Model

The programme is delivered by a single accountable Product Engineer role that carries product ownership, architecture, construction, and quality responsibilities, supported by procured external services for the functions that require independence or specialist depth. Where a lifecycle discipline would normally rely on separation of duties between people, this plan substitutes separation by process: written gate evidence, checklists, decision records, and independent external review at the points of highest risk. No gate passes on assertion.

## 10.2 Responsibilities

| Function | Carried By | How Independence Is Preserved |
| --- | --- | --- |
| Product ownership: backlog, priorities, acceptance | Product Engineer | Acceptance recorded against written criteria per story; increment gates demonstrated on real data and devices, evidenced |
| Architecture and design | Product Engineer | ADR discipline; procured external review for ADR-003 (rendering) and ADR-004 (tenant isolation) |
| Construction | Product Engineer | PR-based change review against checklists; CI gates and release-blocking suites enforce standards mechanically |
| Quality and verification | Product Engineer | Automated suites as the primary verifier; procured external accessibility audit and penetration test at I6; pilot UAT as external validation |
| Legal and compliance | External counsel | Engaged from Stage 2 with monthly checkpoints; sole authority on Gate G5.1 |
| Security assessment | External assessor (I6) + continuous automated scanning | Independent report; criticals closed before G5 |
| Accessibility audit | External auditor (I6) + continuous automated checks | Independent WCAG 2.2 AA report against all guest flows |
| Validation | Pilot couples, planners, vendors, caterers | Real weddings executing real scenarios; retrospectives feed G5.4 |

## 10.3 Decision Authority and Evidence

| Decision | Authority | Evidence Record |
| --- | --- | --- |
| Requirements baseline and changes | Product Engineer (change-control review) | Change log with RTM impact analysis per change |
| Architecture (ADRs, G2) | Product Engineer; external review on ADR-003/004 | Accepted ADR set; prototype measurements |
| Increment acceptance (G3) | Product Engineer | Demonstration record per increment exit criterion |
| V&V acceptance (G4) | Product Engineer on internal results; external reports stand on their own | V&V evidence pack |
| Launch (G5) | Product Engineer; counsel holds G5.1 | Gate review record with all four gate evidences |
| Production incident (S1) | Product Engineer | Post-incident review within five working days |

# 11. CONFIGURATION AND CHANGE MANAGEMENT

## 11.1 Configuration Management

- Configuration items: source (monorepo), OpenAPI contract, ADRs, infrastructure-as-code, database migrations, design tokens/themes, test suites, runbooks, and this document set — all versioned in the repository

- Baselines: requirements baseline (G1), architecture baseline (G2), release baselines (every production promotion, tagged and reproducible)

- Build reproducibility: pinned dependencies, locked toolchains, artefact registry

## 11.2 Change Control

- Requirement changes: change request → RTM impact analysis (scope, schedule, test) → fortnightly change-control review with a written disposition → BRD/US amended first, then backlog

- Architecture changes: new or superseding ADR through the architecture review; construction never diverges silently from an accepted ADR

- Permanent product boundaries (no money movement, no marketplace, no guest accounts, no print) are outside change control by policy

- Emergency changes (S1 fixes) follow an expedited path with retrospective change-control review

## 11.3 Traceability

The RTM links BR → FR → story → design artefact → test case → release. Coverage is reported at every increment gate: any FR without a passing test at its target increment is a gate finding.

# 12. RISK MANAGEMENT

The register carries the engineering-facing view of the BRD risk set with SDLC-stage mitigations. Reviewed fortnightly and at every gate.

| Risk | Impact | Prob. | Stage Mitigation |
| --- | --- | --- | --- |
| Rendering approach misses the performance budget | High | Low | Stage 2 spike with physical-device evidence before any guest-surface construction (G2) |
| Deliverability below 98% at pilot sends | Critical | Medium | Warm-up from Week 1; webhook-verified delivery states in I2; suite-gated |
| Cross-tenant or privacy defect escapes | Critical | Low | Isolation/privacy suites on every merge; threat model; pen test at I6 |
| Velocity shortfall against 318 points | High | Medium | Velocity calibrated at Sprint 4 and re-baselined; schedule absorbs variance, scope does not; the end-of-I2 product is the pre-agreed minimum launchable position if the market window forces an early release |
| Late requirement churn destabilises construction | Medium | Medium | G1 baseline + CCB; changes priced against RTM impact before acceptance |
| Test environment/device lab not ready for I2 | High | Low | Engineering platform is WBS 4.0 in Weeks 1-4; device lab procured during I1 |
| Pilot recruitment shortfall starves validation (G5.4) | High | Medium | Recruitment from I2; varied-stage couples; planner-sourced pilots as backup |
| Commercial decision late; billing unbuilt | Critical | Medium | Decision deadline end of I4 (Week 54); billing sized as I5 scope; G5.2 |
| Legal review slips | Critical | Medium | Counsel checkpoints monthly from Stage 2; G5.1 tracked on the critical path |
| Continuity and single-track concentration | High | Medium | ADRs, runbooks, and decision records keep the system re-learnable; managed services minimise bespoke operations; automated backups verified quarterly; sustained-pace policy with the schedule, not scope, absorbing pressure |

# 13. QUALITY MANAGEMENT SUMMARY

- Quality is built in through stage gates (G1-G5), the Definition of Done, CI quality gates, and the four release-blocking suites — not inspected in at the end

- Independent verification: procured external accessibility audit and penetration test at I6; procured external review of the two highest-risk ADRs at G2

- Metrics reviewed at each sprint close: CI pass rate, escaped-defect count by severity, test coverage on critical modules, deployment frequency, change-failure rate, mean time to restore, SLO attainment from first pilot

- Every gate produces a written evidence record; no gate passes on assertion

# 14. APPENDICES

## Appendix A: Gate Summary

| Gate | Name | When | Pass Condition |
| --- | --- | --- | --- |
| G1 | Requirements Baseline | Week 2 | Baseline signed; RTM complete; criteria testable |
| G2 | Architecture Baseline | Week 5-6 | ADRs accepted; performance prototype proven; security design signed |
| G3 | Increment Exit (x5) | Wk 14/32/44/54/66 | Increment demonstration on real data and devices; increment-scope verification complete |
| G4 | V&V Complete | Week 72 | Audits, pen test, load test, field NFRs, UAT acceptance — evidence pack |
| G5 | Release / Launch | Week 72+ | Legal, commercial, quality, validation gates passed |

## Appendix B: Tooling Baseline

| Concern | Tooling (finalised in Stage 2) |
| --- | --- |
| Tracker / backlog / RTM | Issue tracker with requirement linking (e.g. Jira/Linear) |
| Repository / CI | Monorepo host with PR checks and pipelines |
| Observability | Metrics, logs, traces, real-user monitoring, external probes |
| Device lab | Physical Android/iOS reference set + screen readers + network throttling |
| Load testing | Scriptable load rig against staging with production-shaped data |
| Feature flags | Server-evaluated flag service with tenant targeting |

## Appendix C: Increment-to-Epic Traceability

| Increment | Epics (US v1.0) | Stories |
| --- | --- | --- |
| I1 | 1, 2 (excl. handoff), 3, 4 (excl. run sheet), 15 (skeleton) | US-001..007, US-009..014, US-049 (partial) |
| I2 | 5, 6, 7 (core), 8 | US-018, US-020..026, US-028..031 |
| I3 | 4 (run sheet), 7 (remainder), 9, 10, 11 | US-015, US-019, US-027, US-032..039 |
| I4 | 2 (handoff), 12, 13 | US-008, US-040..045 |
| I5 | 14, 15 (completion) | US-046..051 scope |
| I6 | — (verification only) | — |

## Appendix D: Document Review Log

| Date | Reviewer | Section | Comment | Resolution |
| --- | --- | --- | --- | --- |